## Slide 1: Delivery plan: 12 two-week sprints
A working demo and a milestone sign-off with Memorial Hermann at the end of every sprint
Discover and design
Phase 1 · Classes and events
Phase 2 · Conferences and engagement
Sprint-end milestone
SPRINT 1
Weeks 1-2
Walkthrough, requirements, data model
Design sign-off
SPRINT 2
Weeks 3-4
Environments, CI/CD, security baseline, backlog
Architecture approved
SPRINT 3
Weeks 5-6
Event catalog and class listings on Sitecore
Classes browsable in test
SPRINT 4
Weeks 7-8
Registration, seat holds, waitlist
Registration demo
SPRINT 5
Weeks 9-10
Chase checkout, refunds, confirmation journeys
Pay and confirm end to end
SPRINT 6
Weeks 11-12
QR check-in, reporting, My MH app entry, load test
User testing starts
SPRINT 7
Weeks 13-14
User testing, move upcoming classes, go-live
Phase 1 live
SPRINT 8
Weeks 15-16
Sessions, tracks, rooms and speakers
Conference build demo
SPRINT 9
Weeks 17-18
My Agenda portal, ticket types, Authorize.net
Attendee portal demo
SPRINT 10
Weeks 19-20
Badges, CME [to confirm], PEI journeys
Engagement journeys pilot
SPRINT 11
Weeks 21-22
Certain data migration, load test, user testing
Testing sign-off
SPRINT 12
Weeks 23-24
Go-live, hypercare, knowledge transfer
Phase 2 live, Certain retired
Notes: Two-week sprints, each closing with a demo and a milestone Memorial Hermann signs off. Sprints 1 and 2 cover discovery and design, sprints 3 to 7 deliver classes and events (live at week 14), and sprints 8 to 12 deliver conferences and the first engagement journeys (live at week 24, Certain retired). Sprint scope is refined after the current-state walkthrough.

## Slide 2: A dedicated five-person delivery pod
1
1
3
LEAD
Scrum Master or Project Manager
Runs sprints, milestones, risks and status
QUALITY
QA Engineer
Test plans, automation, load tests, user testing support
BUILD
2 Salesforce Developers + 1 Marketing Cloud Developer
Event app, registration, payments, integrations, journeys and PEIs
Every two-week sprint
Plan
Sprint planning with your product owner
Build and test
Daily stand-ups; QA inside the sprint
Demo
Sprint review and milestone sign-off
Improve
Retrospective; adjust the next sprint
FROM MEMORIAL HERMANN
A product owner, plus an Epic and app contact from Lucky Rai’s team
5 people · 12 sprints · 24 weeks
Notes: A small, dedicated pod: one Scrum Master or Project Manager leading delivery, one QA engineer embedded in every sprint, and a build team of two Salesforce developers and one Marketing Cloud developer. Memorial Hermann provides a product owner and an Epic and app contact.

## Slide 3: Investment
Fixed-scope delivery by the five-person pod across 12 sprints
STANDARD PROGRAM VALUE
$700,000
STRATEGIC PARTNER INVESTMENT
$350,000
50% partnership credit, applied upfront
You save $350,000 on the full program
Phase
Sprints
Standard
Partner
Phase 1 · Classes and events
1-7
$410,000
$205,000
Phase 2 · Conferences and engagement
8-12
$290,000
$145,000
Total program
12 sprints
$700,000
$350,000
Included
Dedicated five-person pod for 24 weeks
Sprint demos and milestone sign-offs
Testing, load testing, go-live and hypercare
Documentation and handover to your admins
Not included
Salesforce licenses (Shield, Agentforce, Data Cloud)
Payment gateway transaction fees
Waiting room subscription
Indicative pricing, billed at sprint milestones. Final commercials confirmed in the statement of work.
Notes: Standard program value is $700,000. As a strategic partner, Memorial Hermann receives a 50% partnership credit applied upfront, for an investment of $350,000. Billing follows sprint milestones. Licenses and third-party fees are outside this price.